## Dashboard
GTA Construction Project Cost & Performance Dashboard
Total # Projects | Total Budget (CAD) | Total Actual Cost (CAD) | Avg Cost Variance %
50 | 1213237564.42 | 1392810833.71 | 15.828
Budget VS Actual Cost by Project type
% Cost Variance by Region
Project Status
% Cost Variance b y Project Trype
This shape represents a slicer. Slicers are supported in Excel 2010 or later. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2003 or earlier, the slicer cannot be used.
This shape represents a slicer. Slicers are supported in Excel 2010 or later. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2003 or earlier, the slicer cannot be used.

## construction_projects
Project_ID | Project_Name | Project_Type | Region | Phase | Status | Planned_Budget_CAD | Actual_Cost_CAD | Cost_Variance_CAD | Cost_Variance_Pct | Labor_Cost_CAD | Material_Cost_CAD | Subcontractor_Cost_CAD | Start_Date | Planned_End_Date | Actual_End_Date | Delay_Days | Completion_Pct | Risk_Level | Project_Manager
PRJ-001 | Toronto Retail Complex 1 | Retail Complex | Toronto | Closeout | Completed | 1738032.38 | 1842334.71 | 104302.33 | 6 | 789322.35 | 584734.5 | 468277.86 | 2022-08-17 | 2023-04-06 | 2023-07-01 | 86 | 34 | Medium | Sarah Chen
PRJ-002 | Mississauga Residential High-Rise 2 | Residential High-Rise | Mississauga | Finishing | Completed | 12016714.22 | 14309593.32 | 2292879.1 | 19.1 | 4778029.94 | 5578477.75 | 3953085.63 | 2023-07-29 | 2024-05-17 | 2024-08-14 | 89 | 30 | Medium | James Okafor
PRJ-003 | Vaughan Retail Complex 3 | Retail Complex | Vaughan | Pre-Construction | Completed | 17342400.57 | 17553835.65 | 211435.08 | 1.2 | 5648751.92 | 6473699.14 | 5431384.59 | 2022-12-11 | 2023-06-23 | 2023-06-23 | 0 | 35 | Medium | Mark Johnson
PRJ-004 | Hamilton Industrial Warehouse 4 | Industrial Warehouse | Hamilton | Closeout | Completed | 6678895.06 | 8808915.91 | 2130020.85 | 31.9 | 3291926.67 | 4160815.5 | 1356173.74 | 2022-03-22 | 2024-01-06 | 2024-01-06 | 0 | 54 | High | Mark Johnson
PRJ-005 | Toronto Residential High-Rise 5 | Residential High-Rise | Toronto | Structure | Completed | 33232534.27 | 41847315.61 | 8614781.34 | 25.9 | 14256629.71 | 19535251.14 | 8055434.76 | 2022-03-23 | 2023-02-14 | 2023-04-03 | 48 | 77 | Low | Maria Santos
PRJ-006 | Ottawa Commercial Office 6 | Commercial Office | Ottawa | Finishing | Completed | 13715402.19 | 18168269.83 | 4452867.64 | 32.5 | 7191461.94 | 6044229.07 | 4932578.82 | 2023-10-26 | 2024-04-06 | 2024-04-27 | 21 | 64 | Medium | Mark Johnson
PRJ-007 | Hamilton Retail Complex 7 | Retail Complex | Hamilton | Structure | Completed | 11370951.11 | 12277364.8 | 906413.69 | 8 | 4054390.49 | 3845733.77 | 4377240.54 | 2022-02-27 | 2023-01-17 | 2023-04-30 | 103 | 70 | High | James Okafor
PRJ-008 | Vaughan Retail Complex 8 | Retail Complex | Vaughan | Foundation | Completed | 20083779.1 | 26426618.85 | 6342839.75 | 31.6 | 10544162.69 | 10776655.14 | 5105801.02 | 2023-04-15 | 2023-12-07 | 2023-12-07 | 0 | 84 | High | Lisa Patel
PRJ-009 | Brampton Industrial Warehouse 9 | Industrial Warehouse | Brampton | Pre-Construction | Completed | 11356377.58 | 15319924.18 | 3963546.6 | 34.9 | 6468387.3 | 5064280.74 | 3787256.14 | 2023-06-06 | 2025-01-21 | 2025-01-21 | 0 | 84 | Low | Lisa Patel
PRJ-010 | Vaughan Residential High-Rise 10 | Residential High-Rise | Vaughan | Pre-Construction | Completed | 19390154.68 | 26146626 | 6756471.32 | 34.8 | 10094079.68 | 8443016.12 | 7609530.2 | 2023-06-26 | 2024-06-07 | 2024-09-25 | 110 | 64 | High | Mark Johnson
PRJ-011 | Toronto Infrastructure 11 | Infrastructure | Toronto | Finishing | Completed | 15028256.37 | 15227577.66 | 199321.29 | 1.3 | 6127462.13 | 6114425.72 | 2985689.81 | 2022-01-04 | 2024-04-12 | 2024-05-15 | 33 | 68 | Low | Mark Johnson
PRJ-012 | Hamilton Mixed-Use Development 12 | Mixed-Use Development | Hamilton | Finishing | Completed | 10346099.54 | 11376214.54 | 1030115 | 10 | 4933849.44 | 4775608.78 | 1666756.32 | 2022-06-15 | 2024-03-18 | 2024-07-14 | 118 | 32 | Medium | Sarah Chen
PRJ-013 | Brampton Infrastructure 13 | Infrastructure | Brampton | Mechanical/Electrical | Completed | 12352889.36 | 12925428.94 | 572539.58 | 4.6 | 5340847.35 | 6405802.5 | 1178779.09 | 2023-08-04 | 2024-01-21 | 2024-01-21 | 0 | 46 | High | James Okafor
PRJ-014 | Vaughan Retail Complex 14 | Retail Complex | Vaughan | Finishing | Completed | 47369009.65 | 48129319.37 | 760309.72 | 1.6 | 19302409.81 | 21079367.73 | 7747541.83 | 2023-06-25 | 2025-06-05 | 2025-07-02 | 27 | 69 | High | David Kim
PRJ-015 | Ottawa Retail Complex 15 | Retail Complex | Ottawa | Pre-Construction | Completed | 18984314.88 | 24866521.96 | 5882207.08 | 31 | 7898032.9 | 10385794.92 | 6582694.14 | 2023-04-08 | 2023-11-07 | 2023-11-07 | 0 | 58 | Low | Sarah Chen
PRJ-016 | Ottawa Residential High-Rise 16 | Residential High-Rise | Ottawa | Foundation | Completed | 31739596.38 | 33059224.49 | 1319628.11 | 4.2 | 10106054.6 | 13127252.73 | 9825917.16 | 2022-02-02 | 2023-04-06 | 2023-04-06 | 0 | 46 | High | Mark Johnson
PRJ-017 | Hamilton Mixed-Use Development 17 | Mixed-Use Development | Hamilton | Closeout | Completed | 23897215.8 | 30202442.89 | 6305227.09 | 26.4 | 10154370.47 | 11619354.7 | 8428717.72 | 2023-02-21 | 2023-12-02 | 2023-12-02 | 0 | 36 | Medium | Mark Johnson
PRJ-018 | Ottawa Retail Complex 18 | Retail Complex | Ottawa | Foundation | Completed | 5371684.62 | 5968202.21 | 596517.59 | 11.1 | 2132182.92 | 1957787.92 | 1878231.37 | 2022-12-14 | 2023-07-03 | 2023-07-03 | 0 | 65 | Low | David Kim
PRJ-019 | Toronto Commercial Office 19 | Commercial Office | Toronto | Finishing | Completed | 22434971.88 | 29042960.46 | 6607988.58 | 29.5 | 12116883.33 | 14341392.14 | 2584684.99 | 2023-07-18 | 2024-01-24 | 2024-01-24 | 0 | 51 | Low | David Kim
PRJ-020 | Vaughan Industrial Warehouse 20 | Industrial Warehouse | Vaughan | Mechanical/Electrical | Completed | 11080491.31 | 12303956.14 | 1223464.83 | 11 | 3728598.39 | 5620620.9 | 2954736.85 | 2022-03-02 | 2022-11-15 | 2022-11-15 | 0 | 66 | Medium | David Kim
PRJ-021 | Ottawa Retail Complex 21 | Retail Complex | Ottawa | Foundation | Completed | 49773423.13 | 58349748.74 | 8576325.61 | 17.2 | 25892226.79 | 24263929.51 | 8193592.44 | 2023-05-14 | 2024-01-17 | 2024-01-17 | 0 | 37 | High | Mark Johnson
PRJ-022 | Toronto Infrastructure 22 | Infrastructure | Toronto | Finishing | Completed | 2982045.69 | 3401665.46 | 419619.77 | 14.1 | 904918.85 | 1146922.51 | 1349824.1 | 2023-06-28 | 2024-03-05 | 2024-03-05 | 0 | 38 | High | Mark Johnson
PRJ-023 | Vaughan Commercial Office 23 | Commercial Office | Vaughan | Pre-Construction | Completed | 6434387.39 | 8404049.41 | 1969662.02 | 30.6 | 2805649.73 | 3502256.97 | 2096142.71 | 2022-09-10 | 2024-07-23 | 2024-10-10 | 79 | 70 | High | Maria Santos
PRJ-024 | Ottawa Commercial Office 24 | Commercial Office | Ottawa | Mechanical/Electrical | Completed | 35951494.14 | 37586366.08 | 1634871.94 | 4.5 | 11773381.89 | 16927880.63 | 8885103.56 | 2023-02-10 | 2023-09-22 | 2023-10-30 | 38 | 31 | Low | David Kim
PRJ-025 | Hamilton Mixed-Use Development 25 | Mixed-Use Development | Hamilton | Structure | Completed | 49806774.17 | 48775987.54 | -1030786.63 | -2.1 | 20787000.88 | 23210251.14 | 4778735.52 | 2022-08-07 | 2024-04-06 | 2024-04-06 | 0 | 66 | Medium | James Okafor
PRJ-026 | Hamilton Industrial Warehouse 26 | Industrial Warehouse | Hamilton | Finishing | Completed | 35325226.29 | 42202027.17 | 6876800.88 | 19.5 | 13077384.84 | 18259877.87 | 10864764.46 | 2023-11-01 | 2025-07-24 | 2025-07-24 | 0 | 63 | Low | Sarah Chen
PRJ-027 | Ottawa Residential High-Rise 27 | Residential High-Rise | Ottawa | Closeout | Completed | 27884570.22 | 29528066.85 | 1643496.63 | 5.9 | 11127580.88 | 10417406.91 | 7983079.06 | 2023-09-12 | 2024-07-13 | 2024-08-08 | 26 | 62 | Medium | Sarah Chen
PRJ-028 | Ottawa Residential High-Rise 28 | Residential High-Rise | Ottawa | Structure | Completed | 21467000.74 | 22769448.53 | 1302447.79 | 6.1 | 6428188.63 | 8842904.75 | 7498355.15 | 2022-01-04 | 2023-03-11 | 2023-05-31 | 81 | 84 | High | Lisa Patel
PRJ-029 | Toronto Residential High-Rise 29 | Residential High-Rise | Toronto | Structure | Completed | 4224571.07 | 5505640.8 | 1281069.73 | 30.3 | 2017827.89 | 1814762.48 | 1673050.43 | 2022-06-02 | 2024-03-11 | 2024-03-11 | 0 | 35 | Low | Maria Santos
PRJ-030 | Toronto Infrastructure 30 | Infrastructure | Toronto | Finishing | Completed | 44996769.51 | 46528037.26 | 1531267.75 | 3.4 | 19859419.78 | 17739999.65 | 8928617.83 | 2022-09-13 | 2024-10-24 | 2024-10-24 | 0 | 49 | High | James Okafor
PRJ-031 | Mississauga Commercial Office 31 | Commercial Office | Mississauga | Closeout | Completed | 44130102.13 | 42361126.9 | -1768975.23 | -4 | 17910826.92 | 19577189.01 | 4873110.97 | 2022-12-07 | 2025-05-16 | 2025-08-26 | 102 | 50 | Medium | Mark Johnson
PRJ-032 | Vaughan Residential High-Rise 32 | Residential High-Rise | Vaughan | Structure | Completed | 43672255.75 | 56487324.59 | 12815068.84 | 29.3 | 17569714.26 | 25931585.25 | 12986025.08 | 2022-08-16 | 2023-06-06 | 2023-08-03 | 58 | 58 | Low | Sarah Chen
PRJ-033 | Mississauga Retail Complex 33 | Retail Complex | Mississauga | Closeout | Completed | 20224065.94 | 21466657.31 | 1242591.37 | 6.1 | 7553711.74 | 9357393.71 | 4555551.86 | 2022-03-13 | 2024-08-10 | 2024-08-10 | 0 | 72 | High | Sarah Chen
PRJ-034 | Brampton Residential High-Rise 34 | Residential High-Rise | Brampton | Mechanical/Electrical | Completed | 9339106.9 | 12467835.9 | 3128729 | 33.5 | 3978953.01 | 5701362.26 | 2787520.63 | 2022-09-29 | 2023-02-05 | 2023-02-05 | 0 | 95 | Medium | Sarah Chen
PRJ-035 | Hamilton Industrial Warehouse 35 | Industrial Warehouse | Hamilton | Finishing | Completed | 9908899.34 | 9589383.05 | -319516.29 | -3.2 | 3714653.02 | 4680123.56 | 1194606.47 | 2023-03-23 | 2023-06-22 | 2023-10-03 | 103 | 55 | High | Maria Santos
PRJ-036 | Toronto Industrial Warehouse 36 | Industrial Warehouse | Toronto | Closeout | Completed | 47469287.06 | 62579157.14 | 15109870.08 | 31.8 | 26909623.75 | 25120806.92 | 10548726.47 | 2023-10-01 | 2024-11-15 | 2024-11-30 | 15 | 82 | High | Maria Santos
PRJ-037 | Ottawa Industrial Warehouse 37 | Industrial Warehouse | Ottawa | Closeout | Completed | 15134932.53 | 15148782.8 | 13850.27 | 0.1 | 6522476.72 | 6409495.19 | 2216810.89 | 2023-03-07 | 2025-04-15 | 2025-07-10 | 86 | 81 | Medium | Lisa Patel
PRJ-038 | Brampton Residential High-Rise 38 | Residential High-Rise | Brampton | Mechanical/Electrical | Completed | 14702228.99 | 16495243.15 | 1793014.16 | 12.2 | 5582517.47 | 5653584.26 | 5259141.42 | 2023-08-17 | 2025-07-28 | 2025-09-25 | 59 | 51 | Medium | Mark Johnson
PRJ-039 | Brampton Residential High-Rise 39 | Residential High-Rise | Brampton | Foundation | Completed | 26014874.49 | 31300481.53 | 5285607.04 | 20.3 | 12036886.07 | 10796416.66 | 8467178.8 | 2022-12-10 | 2023-06-13 | 2023-09-17 | 96 | 48 | Low | Sarah Chen
PRJ-040 | Mississauga Residential High-Rise 40 | Residential High-Rise | Mississauga | Finishing | Completed | 49204833.13 | 58775645.01 | 9570811.88 | 19.5 | 16979522.54 | 25818427.55 | 15977694.92 | 2022-03-16 | 2023-09-23 | 2023-12-12 | 80 | 81 | Medium | James Okafor
PRJ-041 | Ottawa Commercial Office 41 | Commercial Office | Ottawa | Closeout | Completed | 34537309.45 | 45142471.44 | 10605161.99 | 30.7 | 15961996.45 | 13996137.84 | 15184337.15 | 2022-04-20 | 2024-09-23 | 2024-10-15 | 22 | 45 | Low | David Kim
PRJ-042 | Vaughan Commercial Office 42 | Commercial Office | Vaughan | Mechanical/Electrical | Completed | 33545097.76 | 45123422.44 | 11578324.68 | 34.5 | 16809849.52 | 20028247.29 | 8285325.63 | 2023-09-02 | 2024-10-20 | 2025-02-11 | 114 | 84 | High | Lisa Patel
PRJ-043 | Mississauga Industrial Warehouse 43 | Industrial Warehouse | Mississauga | Closeout | Completed | 37310944.39 | 42529617.78 | 5218673.39 | 14 | 12991193.62 | 19373728.03 | 10164696.13 | 2022-09-23 | 2025-01-29 | 2025-01-29 | 0 | 60 | Medium | Maria Santos
PRJ-044 | Toronto Industrial Warehouse 44 | Industrial Warehouse | Toronto | Foundation | Completed | 35820470.7 | 37389315.3 | 1568844.6 | 4.4 | 10475219.83 | 14081080.05 | 12833015.42 | 2022-12-10 | 2024-01-31 | 2024-02-10 | 10 | 57 | Low | Sarah Chen
PRJ-045 | Vaughan Industrial Warehouse 45 | Industrial Warehouse | Vaughan | Finishing | Completed | 16878628.86 | 19180362.77 | 2301733.91 | 13.6 | 8424253.29 | 5829034.83 | 4927074.65 | 2022-03-05 | 2022-12-31 | 2023-02-18 | 49 | 78 | High | David Kim
PRJ-046 | Brampton Residential High-Rise 46 | Residential High-Rise | Brampton | Finishing | Completed | 15281326.29 | 16901065.26 | 1619738.97 | 10.6 | 7260059.95 | 6720639.23 | 2920366.08 | 2023-03-06 | 2024-12-06 | 2025-02-13 | 69 | 85 | Medium | David Kim
PRJ-047 | Vaughan Residential High-Rise 47 | Residential High-Rise | Vaughan | Mechanical/Electrical | Completed | 17138412.41 | 20937257.27 | 3798844.86 | 22.2 | 9084850.21 | 10387902.85 | 1464504.21 | 2023-02-19 | 2025-05-30 | 2025-05-30 | 0 | 33 | High | David Kim
PRJ-048 | Hamilton Mixed-Use Development 48 | Mixed-Use Development | Hamilton | Pre-Construction | Completed | 33318487.96 | 32771364.56 | -547123.4 | -1.6 | 9897976.62 | 11976968.09 | 10896419.85 | 2023-03-15 | 2023-10-29 | 2023-11-21 | 23 | 71 | Medium | Maria Santos
PRJ-049 | Brampton Industrial Warehouse 49 | Industrial Warehouse | Brampton | Finishing | Completed | 37724486.27 | 48391828.47 | 10667342.2 | 28.3 | 12602060.68 | 23730575.44 | 12059192.35 | 2022-09-16 | 2023-03-08 | 2023-06-11 | 95 | 38 | Low | Mark Johnson
PRJ-050 | Toronto Residential High-Rise 50 | Residential High-Rise | Toronto | Foundation | Completed | 47505780.77 | 48918805.68 | 1413024.91 | 3 | 16862909.72 | 15794800.72 | 16261095.24 | 2022-01-21 | 2024-01-17 | 2024-01-17 | 0 | 89 | Low | Mark Johnson

## Budget vs Actual cost by Projec
Budget vs Actual cost by Project Type
Project_Type | Sum of Planned_Budget_CAD | Sum of Actual_Cost_CAD
Commercial Office | 190748764.94 | 225828666.56
Industrial Warehouse | 264688639.39 | 313443270.71
Infrastructure | 75359960.93 | 78082709.32
Mixed-Use Development | 117368577.47 | 123126009.53
Residential High-Rise | 372813960.31 | 435449573.99
Retail Complex | 192257661.38 | 216880603.6
Grand Total | 1213237564.42 | 1392810833.71

## Cost Variance % by Region
Average of Cost_Variance_Pct
Region | Total
Brampton | 20.6286
Hamilton | 11.1125
Mississauga | 10.94
Ottawa | 14.33
Toronto | 14.97
Vaughan | 21.04
Grand Total | 15.828

## Project Status
Count of Project_ID
Status | Total
Completed | 50
Grand Total | 50

## Cost Breakdown
Data
Project_Type | Sum of Labor_Cost_CAD | Sum of Material_Cost_CAD | Sum of Subcontractor_Cost_CAD
Commercial Office | 84570049.78 | 94417332.95 | 46841283.83
Industrial Warehouse | 108205778.11 | 132330439.03 | 72907053.57
Infrastructure | 32232648.11 | 31407150.38 | 14442910.83
Mixed-Use Development | 45773197.41 | 51582182.71 | 25770629.41
Residential High-Rise | 148163804.56 | 174563790.66 | 112721978.77
Retail Complex | 83815191.61 | 88725096.34 | 44340315.65
Grand Total | 502760669.58 | 573025992.07 | 317024172.06

## Delays by Project Type
Average of Delay_Days
Project_Type | Total
Commercial Office | 53.7143
Industrial Warehouse | 32.5455
Infrastructure | 8.25
Mixed-Use Development | 35.25
Residential High-Rise | 47.7333
Retail Complex | 24
Grand Total | 36.8

## Risk Distribution
Data
Risk_Level | Count of Project_ID | Average of Cost_Variance_Pct
High | 18 | 16.2833
Low | 15 | 20.2667
Medium | 17 | 11.4294
Grand Total | 50 | 15.828

## Variance by Project Type
Average of Cost_Variance_Pct
Project_Type | Total
Commercial Office | 22.6143
Industrial Warehouse | 16.9364
Infrastructure | 5.85
Mixed-Use Development | 8.175
Residential High-Rise | 18.46
Retail Complex | 12.6444
Grand Total | 15.828